AI Employment Navigator

30-Day Pilot Implementation Plan

Developed by Ryan Uher | AI Employment Navigator

# Pilot Objective

Determine whether a standardized AI-assisted employment workflow can improve the quality and efficiency of job discovery and application support while maintaining appropriate human oversight and privacy safeguards.

# Pilot Scope

Approximately 10 clients

Small group of participating career planners

30 calendar days

Use organization-approved AI platforms only

NEworks included as one source alongside broader job-market sources

Manual verification of important job facts before client action

# Week 1 - Setup

Select clients representing a reasonable range of employment goals.

Complete client intake and candidate profiles.

Set salary, geography, job-family, exclusion and priority-employer rules.

Run manual test searches and refine weak criteria.

Document baseline staff/client job-search process and estimated time spent.

# Week 2 - Active Job Watch

Begin recurring searches where the selected platform supports them.

Use manual searches where recurring tasks are unavailable.

Review new leads with clients.

Track qualified leads, poor matches, duplicates and jobs the client chooses to pursue.

Begin application support for selected opportunities.

# Week 3 - Application & Interview Support

Continue multi-source discovery.

Use resume alignment and application prompts with clients.

Use employer research and interview preparation when interviews occur.

Document AI errors, hallucinations, outdated postings or missing requirements.

Collect mid-pilot feedback from planners and clients.

# Week 4 - Measure & Evaluate

Continue searches and support.

Compile lead, application, interview and offer data.

Compare time spent and lead quality to baseline.

Identify repeated strengths and weaknesses in the workflow.

Prepare recommendations for expansion, revision or discontinuation.

# Minimum Data to Track

| Data Point | Example | Purpose |
| --- | --- | --- |
| Job surfaced | Operations Coordinator | Volume/quality |
| Source | Employer career page | Source effectiveness |
| Client decision | Applied / declined | Lead usefulness |
| Application date | 8/20/2026 | Activity |
| Employer response | Screen / rejection / none | Conversion |
| Interview stage | First / final | Progress |
| Offer | Yes / no | Outcome |
| Poor-match reason | License required | AI quality control |
| Planner time | 15 minutes | Efficiency |

# Pilot Guardrails

No unnecessary sensitive participant information.

No AI-generated eligibility or sanction decisions.

No fabricated resume content.

No automatic application submission without client review.

No claim that every internet job source is covered.

Verify salary, closing date and mandatory qualifications before recommending action.

# End-of-Pilot Deliverable

Project Lead prepares a short report summarizing outcomes, time/efficiency observations, lead quality, errors/limitations, staff and client feedback, and a recommendation for the next phase.